Project planner uses periods for intervals. Start=1 is period 1 and duration=5 means project spans 5 periods starting from start period. Enter data starting in B5 to update the chart
Title of the project. Enter a new title in this cell. Highlight a period in H2. Chart legend is in J2 to AI2
Select a period to highlight in H2. A Chart legend is in J2 to AI2
Enter activity in column B, starting with cell B5
Enter plan start period in column C, starting with cell C5
Enter plan duration period in column D, starting with cell D5
Enter actual start period in column E, starting with cell E5
Enter actual duration period in column F, starting with cell F5
Enter the percentage of project completed in column G, starting with cell G5
Enter a period in the range of 1 to 60 or select a period from the list. Press ALT+DOWN ARROW to navigate the list, then ENTER to select a value
Type a value from 1 to 60 or select a period from the list-press CANCEL, ALT+DOWN ARROW, then ENTER to select a value
Periods are charted from 1 to 60 starting from cell H4 to cell BO4
This legend cell indicates plan duration
This legend cell indicates actual duration
This legend cell indicates the percentage of project completed
This legend cell indicates actual duration beyond plan
This legend cell indicates the percentage of project completed beyond plan
## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows.					Period Highlight:	1			Plan Duration					Actual Start					% Complete					Actual (beyond plan)					% Complete (beyond plan)
Feature	PLAN START	PLAN DURATION	ACTUAL START	ACTUAL DURATION	Main Contributor	PERCENT COMPLETE	PERIODS
					1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60
Login	1	7	1	14	Everyone	100%
Logout	1	7	1	14	Everyone	100%
Create User	1	7	1	14	Everyone	100%
Delete User	1	7	1	14	Everyone	100%
User Profile	7	7	14	9	Richard	70%
User Ratings	7	7	14	14		0%
Seller Account	7	7	14	9	Ahn/Minh	50%
Item Display	7	14	5	14	Jeff	7500%
Upload Items to sell	14	14	5	7	Ahn	50%
Search Bar	14	14	6	7	Minh	80%
Related Items/Categories	14	14	5	7	Jeff	50%
Checkout	14	7	14	1	Jeff	75%
Related Items	14	7	21	7		0%
Dark Mode	21	7	21	7		0%
Discount	21	7	21	7		0%
Image Zoom	21	7	21	7		0%